## Frontend Tasks
Task ID | Module | Task | Details / Acceptance criteria | SRS Ref | Priority | Status | Done By | Date Done | Notes
FE-001 | 1. Setup & Foundation | Initialise React project and folder structure | Vite + React app with assets, components, pages, services, data, hooks, context, routes, utils folders. App runs with npm run dev. | CON-01, NFR-MAIN-01 | Must | Done | aminullah-01 | 2026-09-22 | Vite + React app initialised with modular folder structure. npm run dev and build verified.
FE-002 | 1. Setup & Foundation | Configure ESLint, Prettier and pre-commit checks | Lint and format scripts pass on a clean checkout; hook blocks commits that fail lint. | NFR-MAIN-03 | Should | Done | aminullah-01 | 2026-09-25 | Configured ESLint 9, Prettier, lint-staged, and Husky pre-commit hook. Verified pre-commit blocks lint failures and scripts pass.
FE-003 | 1. Setup & Foundation | Environment configuration | Create .env.example with API base URL and a mock/API switch. No secrets committed. | NFR-MAIN-02, NFR-SEC-09 | Must | Done | aminullah-01 | 2026-09-25 | Created .env.example and .env with VITE_API_BASE_URL and VITE_USE_MOCK_DATA switch. Verified .env is gitignored and src/utils/env.js works.
FE-004 | 1. Setup & Foundation | Set up routing with full route map | React Router routes for public, buyer, seller, admin and error pages exactly as in SRS 4.1.2. | SRS 4.1.2 | Must | Done | aminullah-01 | 2026-09-27 | Implemented React Router route map for all public, buyer, seller, admin and error routes matching SRS 4.1.2 with layout shells.
FE-005 | 1. Setup & Foundation | Design tokens and global styles | Colours, typography, spacing, breakpoints defined once; consistent across all roles. | UI-02 | Must | Done | aminullah-01 | 2026-09-27 | Defined design tokens in src/utils/tokens.js and CSS custom properties in src/index.css for colours, typography, 8px spacing, and 360-1920px breakpoints.
FE-006 | 1. Setup & Foundation | Responsive layout shell | Layout works from 360 px to 1920 px with no horizontal page scroll (breakpoints 360/768/1024/1280). | NFR-COMP-02, UI-04 | Must | Done | aminullah-01 | 2026-09-27 | Implemented responsive layout shells (MainLayout with hamburger drawer, DashboardLayout with off-canvas sidebar), table-responsive wrappers, and 360-1920px overflow protections.
FE-007 | 1. Setup & Foundation | Formatting utilities (currency, dates) | Prices show as ₦2,500 with unit; timestamps stored UTC, displayed Africa/Lagos. | NFR-USAB-04, NFR-LOC-02 | Must | Done | aminullah-01 | 2026-09-27 | Created formatters in src/utils/formatters.js: formatCurrency, formatPrice (₦2,500 / basket), formatDate/formatDateTime (Africa/Lagos WAT), and toUtcIso.
FE-008 | 1. Setup & Foundation | UI strings/constants file | User-facing text (incl. standard error messages) kept in one place so translation can be added later. | NFR-LOC-01, ERR-01 | Should | Done
FE-009 | 1. Setup & Foundation | API client wrapper | Base URL, Authorization header, JSON envelope handling, normalised errors (401/403/404/409/422/429/5xx). | IF-01 to IF-05 | Must | Done
FE-010 | 1. Setup & Foundation | Service layer skeleton | productService, categoryService, orderService, authService, sellerService, adminService; components never import mock data directly. | CON-02 | Must | Done
FE-011 | 1. Setup & Foundation | Mock data conforming to API schema | Mock products, sellers, categories, orders match the API/OpenAPI field names and shapes. | IF-06, NFR-MAIN-05 | Must | Done
FE-012 | 1. Setup & Foundation | Mock/API switch | One environment setting flips all services between mock data and the Laravel API with zero component changes. | NFR-MAIN-02 | Must | Done
FE-013 | 1. Setup & Foundation | Auth context | Holds user, role and token; login, logout, session restore on refresh. | AUTH-04, AUTH-05 | Must | Done
FE-014 | 1. Setup & Foundation | Cart context with persistence | Cart survives refresh and browser restart on the same device; storage calls wrapped in try/catch. | CART-06 | Must | Done
FE-015 | 1. Setup & Foundation | Route guards (role-based) | Buyer, Seller and Admin routes blocked for other roles; unauthenticated users sent to login and back. | AUTH-07 | Must | Done
FE-016 | 1. Setup & Foundation | Error boundary and error pages | Friendly 403, 404, 500 pages; session-expired prompt returns user to login and back. | ERR-04 | Should | Done
FE-017 | 1. Setup & Foundation | Loading, empty and error state components | Reusable spinner/skeleton, empty state, and “Unable to load… Try again” with retry. | MKT-10, ERR-01 | Must | Done
FE-018 | 1. Setup & Foundation | Toast/notification component | Success and error toasts used consistently across forms and actions. | ERR-03 | Should | Done
FE-019 | 1. Setup & Foundation | Test framework setup | Vitest/Jest and React Testing Library configured; sample test runs in CI. | NFR-MAIN-04 | Should | Done
FE-020 | 1. Setup & Foundation | CI pipeline | GitHub Actions runs lint, tests and build on every pull request. | NFR-MAIN-07 | Should | Done
FE-021 | 1. Setup & Foundation | Route-level code splitting | Seller and admin dashboards lazy-loaded; initial bundle ≤ 250 KB gzipped. | NFR-PERF-01 | Should | Done
FE-022 | 2. Shared Components | Navbar | Logo, search, categories link, cart with item count, login/register or account menu; options depend on role. | UI-01, UI-07, CART-07 | Must | Done
FE-023 | 2. Shared Components | Footer | Marketplace info and links; content editable from admin settings later. | MKT-01, ADM-08 | Must | Done
FE-024 | 2. Shared Components | Form field components | Input, select, textarea, checkbox with labels, inline validation messages, correct input types and autocomplete. | UI-05, NFR-USAB-05 | Must | Done
FE-025 | 2. Shared Components | Button and link components | Primary/secondary/danger variants; disabled and loading states; touch targets ≥ 44×44 px. | UI-03, NFR-USAB-03 | Must | Done
FE-026 | 2. Shared Components | ProductCard | Image, name, price with unit, seller, location, availability badge, rating, “View Product”. | MKT-02, REV-01 | Must | Done
FE-027 | 2. Shared Components | Availability badge | Shows Available / Out of Stock / Unavailable from stock and availability flag. | SEL-07, BR-01 | Must | Done
FE-028 | 2. Shared Components | Rating display | Shows 0–5 value with one decimal or “No ratings yet”. | REV-01 | Should | Done
FE-029 | 2. Shared Components | Pagination component | Page controls tied to URL; default 12 per page. | MKT-03 | Must | Done
FE-030 | 2. Shared Components | Quantity selector | Min 1, max available stock; disabled when out of stock. | MKT-06, CART-02 | Must | Not Started
FE-031 | 2. Shared Components | Category card/chip | Used on homepage and filter panel; data-driven from API. | MKT-08, MKT-09 | Must | Not Started
FE-032 | 2. Shared Components | Seller card | Business name, location, rating/summary, link to seller profile. | MKT-01, MKT-07 | Should | Done | aminullah-01 | 2026-09-29 | Implemented SellerCard in src/components/products/SellerCard.jsx: business name, location, rating or "No ratings yet", short description and product count, plus a 44px "View Seller" link to /sellers/:id. Data-driven from seller_profiles columns and hides unapproved sellers from public listings (MKT-04). 14 tests added; lint, format, full suite and build pass.
FE-033 | 2. Shared Components | Search bar | Keyword search with submit; used in navbar and hero. | SRCH-01 | Must | Done | aminullah-01 | 2026-09-29 | Implemented shared SearchBar in src/components/common/SearchBar.jsx: keyword field with submit, trimmed/encoded into ?search= on /products (SRCH-01, SRCH-06), URL-synced input, optional clear action and 44px touch targets. Refactored Navbar desktop and mobile drawer to use it (removed duplicate inline forms) and added .search-bar styles. 16 tests added; lint, format, full suite (239 tests) and build pass.
FE-034 | 2. Shared Components | Filter panel | Category, price range, availability, seller, location; collapsible on mobile. | SRCH-02, SRCH-03 | Must | Done
FE-035 | 2. Shared Components | Sort dropdown | Price low→high, high→low, newest (popularity/rating when available). | SRCH-04, SRCH-05 | Must | Done
FE-036 | 2. Shared Components | Modal / confirm dialog | Accessible dialog for delete, cancel and override confirmations. | SEL-04, ORD-07 | Must | Done
FE-037 | 2. Shared Components | Responsive data table | Table that scrolls or turns into cards on tablets; used across dashboards. | NFR-USAB-06 | Must | Done
FE-038 | 2. Shared Components | Order status badge and timeline | Colour-coded status badge; timeline of status history with timestamps. | ORD-02, ORD-06 | Must | Done
FE-039 | 2. Shared Components | Lazy image with placeholder | Lazy-loads below the fold; default placeholder when image missing or fails. | NFR-PERF-03, NFR-COMP-03, SEL-05 | Must | Done
FE-040 | 2. Shared Components | Skeleton loaders | Skeletons for product grid, tables and detail pages. | MKT-10 | Could | Done
FE-041 | 3. Public Pages | Home: hero section with search | Headline, call to action and search box. | MKT-01 | Must | Done
FE-042 | 3. Public Pages | Home: featured products section | Grid of featured/latest products from the service layer. | MKT-01 | Must | Done
FE-043 | 3. Public Pages | Home: categories section | Category cards linking to filtered listing. | MKT-01, MKT-08 | Must | Done
FE-044 | 3. Public Pages | Home: featured sellers section | Seller cards linking to seller profile. | MKT-01 | Should | Done
FE-045 | 3. Public Pages | Home: how it works, benefits and CTA sections | Static content sections per source design; responsive. | MKT-01 | Must | Done
FE-046 | 3. Public Pages | Products listing page | Paginated grid of ProductCards showing only publicly purchasable listings. | MKT-02, MKT-03, MKT-04 | Must | Done
FE-047 | 3. Public Pages | Search, filter and sort wired to URL | Criteria combine and are reflected in the page URL so results can be bookmarked/shared. | SRCH-01 to SRCH-06 | Must | Done
FE-048 | 3. Public Pages | No-results state and clear filters | “No results” message with one-click clear all filters. | SRCH-07, SRCH-08 | Must | Done
FE-049 | 3. Public Pages | Category browsing | Browse by category from homepage and filter panel. | MKT-08 | Must | Done
FE-050 | 3. Public Pages | Product details page | Name, image, description, price, unit, stock, seller, location, availability, rating. | MKT-05 | Must | Done
FE-051 | 3. Public Pages | Product details: add to cart | Quantity selector limited to stock; disabled with “Out of Stock” when unavailable. | MKT-06, CART-01 | Must | Done
FE-052 | 3. Public Pages | Seller profile page | Business name, description, location and that seller’s available products. | MKT-07 | Should | Done
FE-053 | 3. Public Pages | Static policy pages | Terms of use, privacy notice and refund/dispute policy pages (content from project owner). | NFR-SEC-12, OI-10, OI-11 | Should | Done
FE-054 | 4. Cart | Cart page layout | Lines show product, quantity, unit price, subtotal; grand total; continue shopping and checkout buttons. | CART-04, CART-05 | Must | Done
FE-055 | 4. Cart | Add / update / remove cart items | Quantity changes clamp between 1 and stock; remove deletes the line. | CART-01 to CART-03 | Must | Done
FE-056 | 4. Cart | Cart totals calculation utility | Line subtotal = price × qty; total = sum; unit-tested; server value is authoritative. | CART-04, BR-02 | Must | Done
FE-057 | 4. Cart | Empty cart state | Shows “Your cart is empty.” and blocks checkout. | CART-05 | Must | Done
FE-058 | 4. Cart | Cart badge in navbar | Live item count. | CART-07 | Should | Done
FE-059 | 4. Cart | Cart re-validation notices | On checkout, call cart validate; show price/stock changes and unavailable items before proceeding. | CART-08 | Must | Done
FE-060 | 4. Cart | Guest checkout redirect keeps cart | Guest is asked to log in or register and returns to checkout with the cart intact. | CART-09 | Must | Done
FE-061 | 4. Cart | Server-side cart sync (later) | Optional sync of authenticated buyer cart across devices. | CART-10 | Could | Done
FE-062 | 5. Authentication & Account | Buyer registration page | Name, email, phone, password with validation (unique email, ≥ 8 chars with letters and digits). | AUTH-01, AUTH-08 | Must | Done
FE-063 | 5. Authentication & Account | Seller registration page | Buyer fields plus business name, location, description. | AUTH-02 | Must | Done
FE-064 | 5. Authentication & Account | Seller “pending approval” notice | After registration and login, seller sees pending/rejected/suspended status and cannot publish. | AUTH-03, ADM-03 | Must | Done
FE-065 | 5. Authentication & Account | Login page | Email and password; generic “Invalid login credentials.”; role-based redirect after login. | AUTH-04, AUTH-09, AUTH-13 | Must | Done
FE-066 | 5. Authentication & Account | Login throttling and suspended messages | Friendly handling of 429 (too many attempts) and suspended account messages. | AUTH-09, AUTH-12 | Should | Done
FE-067 | 5. Authentication & Account | Forgot and reset password pages | Request link by email; reset form using time-limited token. | AUTH-06 | Should | Done
FE-068 | 5. Authentication & Account | Logout and session-expiry handling | Logout clears token; 401 anywhere returns user to login and back after sign-in. | AUTH-05, ERR-04 | Must | Done
FE-069 | 5. Authentication & Account | Profile page | View/edit name, phone (and business details for sellers); change password. | AUTH-11 | Must | Done
FE-070 | 6. Checkout & Buyer Orders | Checkout page: delivery details form | Recipient name, phone, address (street, town/area, state), optional notes; prefilled from profile. | CHK-02 | Must | Done
FE-071 | 6. Checkout & Buyer Orders | Checkout page: order summary and review | Items, quantities, prices, subtotals, total; explicit confirm step. | CHK-03 | Must | Done
FE-072 | 6. Checkout & Buyer Orders | Checkout stepper | Cart → Delivery details → Review → Confirmation in no more than four steps. | CHK-10 | Should | Done
FE-073 | 6. Checkout & Buyer Orders | Payment method display | Show “Pay on delivery / pay seller directly”; no online payment in 1.0. | CHK-09 | Must | Done
FE-074 | 6. Checkout & Buyer Orders | Place order and handle failures | Handle 409/422 (insufficient stock, price change) with clear per-item messages. | CHK-04, ERR-01 | Must | Done
FE-075 | 6. Checkout & Buyer Orders | Idempotent order submission | Generate checkout reference (UUID), disable submit after click, safe retry. | NFR-REL-04, CHK-05 | Must | Done
FE-076 | 6. Checkout & Buyer Orders | Order confirmation page | Order number(s), items, total, delivery details; cart cleared. | CHK-08 | Must | Done
FE-077 | 6. Checkout & Buyer Orders | My Orders list | Newest first, paginated; order number, date, seller, total, status. | ORD-01 | Must | Done
FE-078 | 6. Checkout & Buyer Orders | Order detail page | Items, delivery details, status timeline with timestamps and cancellation reason. | ORD-02, ORD-07 | Must | Done
FE-079 | 6. Checkout & Buyer Orders | Cancel pending order | Cancel button only while Pending; confirm dialog; refresh status. | ORD-03 | Should | Done
FE-080 | 7. Seller Dashboard | Seller dashboard layout and navigation | Sections: Overview, Products, Add Product, Orders, Inventory, Sales, Profile; responsive sidebar. | SEL-01 | Must | Done
FE-081 | 7. Seller Dashboard | Overview page | New (Pending) orders, low-stock items, latest sales figures. | SEL-13 | Should | Done
FE-082 | 7. Seller Dashboard | My products list | Table with search, availability, stock, edit and delete actions. | SEL-02, SEL-03 | Must | Done
FE-083 | 7. Seller Dashboard | Add product form | Name, category, price (> 0), unit, quantity (≥ 0), description, availability, image; inline validation. | SEL-02 | Must | Done
FE-084 | 7. Seller Dashboard | Product image upload | Client-side check of type (JPEG/PNG/WebP) and size (≤ 2 MB); preview; upload with progress. | SEL-05 | Must | Done
FE-085 | 7. Seller Dashboard | Edit product form | Edit all fields including price and stock; success feedback. | SEL-03, SEL-06 | Must | Done
FE-086 | 7. Seller Dashboard | Delete product | Confirm dialog; product removed from lists (soft delete). | SEL-04 | Must | Done
FE-087 | 7. Seller Dashboard | Availability toggle | Manual on/off; auto “Out of Stock” when quantity is 0. | SEL-07 | Must | Done
FE-088 | 7. Seller Dashboard | Inventory page | Current stock, unit, price, availability, last updated; quick inline stock update. | SEL-08 | Must | Done
FE-089 | 7. Seller Dashboard | Low-stock indicator | Highlight items at or below threshold (default 5). | SEL-09 | Could | Done
FE-090 | 7. Seller Dashboard | Seller orders list | Only own orders; filter by status and date. | SEL-10 | Must | Done
FE-091 | 7. Seller Dashboard | Seller order detail | Items, buyer name/phone, delivery details. | SEL-10 | Must | Done
FE-092 | 7. Seller Dashboard | Order status controls | Only valid next steps offered; cancel requires a reason. | SEL-11, ORD-05, ORD-07 | Must | Done
FE-093 | 7. Seller Dashboard | Sales page | Period selector; total sales (Completed), order count, products sold, recent orders. | SEL-12 | Should | Done
FE-094 | 7. Seller Dashboard | Seller profile edit | Edit business name, location, description, phone. | AUTH-11 | Must | Done
FE-095 | 8. Admin Dashboard | Admin layout and navigation | Sections: Overview, Users, Sellers, Products, Categories, Orders, Settings (+ Audit log). | ADM-01 | Must | Done
FE-096 | 8. Admin Dashboard | Admin overview | Counts of users, sellers, products, orders and total sales. | ADM-10 | Should | Done
FE-097 | 8. Admin Dashboard | Users management page | List, search, view, deactivate/reactivate. | ADM-02 | Must | Done
FE-098 | 8. Admin Dashboard | Sellers management page | Filter by Pending; approve, reject (with reason), suspend, reactivate. | ADM-03 | Must | Done
FE-099 | 8. Admin Dashboard | Products moderation page | View all products; unpublish/remove violating listings. | ADM-04 | Must | Done
FE-100 | 8. Admin Dashboard | Categories management page | Create, edit, deactivate; delete only if unused (show blocked message). | ADM-05 | Must | Not Started
FE-101 | 8. Admin Dashboard | Orders monitoring page | Search by number, buyer, seller, status, date; detail view. | ADM-06 | Must | Not Started
FE-102 | 8. Admin Dashboard | Order status override | Admin-only override with mandatory reason. | ADM-07 | Should | Not Started
FE-103 | 8. Admin Dashboard | Marketplace settings page | Edit site name, contact details, support text, footer content. | ADM-08 | Should | Not Started
FE-104 | 8. Admin Dashboard | Audit log page | Filter by user, action and date; paginated. | ADM-09 | Should | Not Started
FE-105 | 9. API Integration | Integrate authService with API | Register, login, logout, profile, password reset against Laravel; mock switch off. | Section 4.4 | Must | Not Started
FE-106 | 9. API Integration | Integrate product and category services | List with query params, detail, seller product CRUD, image upload, stock update. | Section 4.4 | Must | Not Started
FE-107 | 9. API Integration | Integrate orderService | Create order(s), list/detail scoped by role, status change, cancel, cart validate. | Section 4.4 | Must | Not Started
FE-108 | 9. API Integration | Integrate seller and admin services | Dashboard stats, seller/user status, settings, audit logs. | Section 4.4 | Must | Not Started
FE-109 | 9. API Integration | Token handling and CORS/env setup | Agree token storage with backend (HttpOnly cookie preferred); configure staging/production origins. | NFR-SEC-03, NFR-SEC-10 | Must | Not Started
FE-110 | 9. API Integration | Verify mock data vs OpenAPI schema | Automated check that mock shapes equal API responses; fix drift. | IF-06, NFR-MAIN-05 | Should | Not Started
FE-111 | 9. API Integration | Retry and offline error handling | API unreachable shows friendly message with retry; cart never lost. | NFR-REL-05, MKT-10 | Must | Not Started
FE-112 | 10. Testing, Quality & Release | Unit tests: cart, validation, utilities | ≥ 70% line coverage on business-logic modules. | NFR-MAIN-04 | Should | Not Started
FE-113 | 10. Testing, Quality & Release | Component tests for key components | ProductCard, filters, quantity selector, forms. | Section 8.1 | Should | Not Started
FE-114 | 10. Testing, Quality & Release | E2E: buyer purchase journey | Browse → cart → checkout → confirmation (TC-08 to TC-16). | TC-08 to TC-16 | Must | Not Started
FE-115 | 10. Testing, Quality & Release | E2E: seller product and order flow | Add/edit/delete product, process order (TC-19 to TC-24). | TC-19 to TC-24 | Must | Not Started
FE-116 | 10. Testing, Quality & Release | E2E: admin approval flow | Approve/suspend seller, category management (TC-29 to TC-31). | TC-29 to TC-31 | Should | Not Started
FE-117 | 10. Testing, Quality & Release | Role access checks in the UI | Buyer cannot open /seller or /admin (TC-28). | TC-28, AUTH-07 | Must | Not Started
FE-118 | 10. Testing, Quality & Release | Responsive QA 360–1920 px | No horizontal scroll; all actions usable (TC-33). | NFR-COMP-02, TC-33 | Must | Not Started
FE-119 | 10. Testing, Quality & Release | Cross-browser and device testing | Latest two versions of Chrome, Edge, Firefox, Safari, Chrome Android, Samsung Internet. | NFR-COMP-01 | Must | Not Started
FE-120 | 10. Testing, Quality & Release | Accessibility audit | WCAG 2.1 AA: contrast, keyboard use, focus, labels, alt text. | NFR-USAB-02 | Should | Not Started
FE-121 | 10. Testing, Quality & Release | Performance audit | LCP ≤ 2.5 s on simulated 4G; bundle ≤ 250 KB; images resized and lazy-loaded. | NFR-PERF-01, NFR-PERF-03 | Must | Not Started
FE-122 | 10. Testing, Quality & Release | Front-end security review | No secrets in bundle, XSS-safe rendering, dependency audit (npm audit) clean. | NFR-SEC-06, NFR-SEC-13 | Should | Not Started
FE-123 | 10. Testing, Quality & Release | Usability test with buyers | ≥ 5 first-time buyers; ≥ 80% complete an order unassisted. | NFR-USAB-01 | Must | Not Started
FE-124 | 10. Testing, Quality & Release | Production build and deployment | Deploy React build to static/CDN host from CI with production env settings. | Source §43 | Must | Not Started
FE-125 | 10. Testing, Quality & Release | README and developer documentation | Setup, env variables, folder structure, mock/API switch, coding standards. | NFR-MAIN-01 | Should | Not Started

## Summary
Vegetable Joint — Frontend Progress Summary
All figures update automatically from the “Frontend Tasks” sheet (rows 2–500).
Overall | Count
Total tasks | 125
Done | 0
In Review | 0
In Progress | 0
Blocked | 0
Not Started | 125
% complete | 0%
Module | Total | Done | In Progress | % Done
1. Setup & Foundation | 21 | 0 | 0 | 0%
2. Shared Components | 19 | 0 | 0 | 0%
3. Public Pages | 13 | 0 | 0 | 0%
4. Cart | 8 | 0 | 0 | 0%
5. Authentication & Account | 8 | 0 | 0 | 0%
6. Checkout & Buyer Orders | 10 | 0 | 0 | 0%
7. Seller Dashboard | 15 | 0 | 0 | 0%
8. Admin Dashboard | 10 | 0 | 0 | 0%
9. API Integration | 7 | 0 | 0 | 0%
10. Testing, Quality & Release | 14 | 0 | 0 | 0%
Total | 125 | 0 | 0 | 0%
Priority | Total | Done | In Progress | % Done
Must | 92 | 0 | 0 | 0%
Should | 30 | 0 | 0 | 0%
Could | 3 | 0 | 0 | 0%
Done by person
Type each team member’s name exactly as used in the “Done By” column (yellow cells).
Team member | Tasks done
Done but no name in “Done By” | 0
Should be 0 — such rows are highlighted red in the task sheet.

## How to Use
How to use this tracker
Purpose | Tracks every frontend (React) task for Vegetable Joint, derived from SRS v1.0. Each task links to the SRS requirement(s) it satisfies.
What you edit | Only these columns: Status, Done By, Date Done, Notes. Task/Details/SRS Ref/Priority can be edited by the project lead if scope changes.
Status values | Not Started · In Progress · In Review · Done · Blocked (dropdown).
Priority | Must = required for Release 1.0. Should = target for 1.0. Could = may move later (as defined in SRS section 1.2).
Done By | Type the name of the person who completed the task (e.g. “Amaka O.”). Use the same spelling every time so the Summary sheet can count it.
Date Done | Enter the date the task was completed in yyyy-mm-dd format (e.g. 2026-09-25).
Example (not a real entry) | Task FE-014 “Cart context with persistence” → Status: Done · Done By: Amaka O. · Date Done: 2026-09-25 · Notes: Tested on refresh and browser restart.
Colour cues | Green = Done, amber = In Progress, blue = In Review, red = Blocked. A red “Done By” cell means the task is Done but nobody is named.
Adding tasks | Insert new rows inside the table (before the last row) and copy formatting from a row above; Summary formulas cover rows 2–500. Use the next free Task ID.
Starting status | All tasks start as “Not Started”. The concept document does not record what is already built (a React prototype with mock data exists), so please update Status for work already completed.
Assumptions | Priorities and SRS references come from SRS v1.0. Estimates and assignees are intentionally left out; add columns if your team wants them.
Use in Google Sheets | Google Drive → New → File upload → open this file with Google Sheets (or File → Import). Dropdowns, filters and colours carry over.